## Intro
| Look up code data | #REF! | Look up code data | #REF! | 5 Appendix E - Risk Management Tool.xlsx
Purpose
How This Document Should Be Used
Additional Instructions
Other Details
Low
Medium
High
PROJECT RISK REGISTER
INSTRUCTIONS AND NOTES
This Risk Register is design to support the risk management process for rezoning projects within Council Strategic Planning Teams
Identification, assessment and treatment of risks are integral to the management of Planning Proposal. By identifying potential risks early in the project, decision-makers can formulate a plan to mitigate them.
When identifying the risks and potential treatments to mittigate them, those with relevant expertise should be consulted.
It is the nature of risk and risk management that, sometimes, unexpected problems occur. When this happens it is important that the reasons and circumstances are identified and documented, and taken into account with future risk analyses including updating guidance documents accordingly.
All risk management decisions including risk identification, assessment and management should be recorded. This provides an accountability trail.
This risk register should be used to support rezoning projects identify, manage and monitor project and program risks.
Each project should customise the thresholds in the risk rating tab, to ensure categorisation of risks is tailored appropriately. Ideally this would be undertaken at the start of a project and would include collaboration with relevant stakeholders.
This risk register is structured to be used as a "live" document and updated on a regular basis through the project.
The level of status reporting is subject to the expectation of the business and/or project sponsor (or relevant PMO). Some projects may have other separate reporting requirements.
For enquiries, support, training and general coaching in risk management or project management, please contact:
- Council Risk and Audit Team (if applicable))

## Risk Register
[INSERT PROJECT NAME]
Created | 2022-03-15
Last Modified | 2022-10-06
RISK IDENTIFICATION |  | RISK ANALYSIS |  | RISK TREATMENT
ID | Risk | Impact / Consequences | Risk Rating | Mitigation Strategy (Controls) and Actions | Risk Manager | Action Due By (date)
1 | Government Agencies - TfNSW require additional modelling | Additional time required. Additional expenditure. | Medium | Use Stakeholder Management Matrix. Early engagement meetings. Involve proponent transport planners to enable early response. Elevate to senior level in Council and TfNSW for alternate solution.
2 | Government Agencies - Agencies request extension of time | Program extension with likely time extension beyond LEP making guidelines | Medium | Use Program. Early engagement at pre lodgement phase and upfront communication on timeframes and expectations Proactively follow up 1 week prior to referral response due date
3 | Proponent requests extension of time to respond | Program extension wtih likely time extension beyond LEP Making Guidelines | Low | Routine dialogue with proponent with early advice flagging issues and inadequate information.
4 | Technical error in assessment | Assessment misses critical element of proposal, contravening EP& A Act requirements | Low | Undertake scoping component at commencement of assessment allowing for referral to appropriate internal Council teams. Where expertise gaps identified, seek for budget and appointment of external review.
5 | Proposal impacts Council infrastructure needs not addressed in s7.11 plan or VPA. | Development creates demand for additional Council infrastructure, seeking Council to meet upgrade costs. Time to address extends program beyond required timeframe. | High | Undertake detailed infrastructure review of s7.11 plan and seek from proponent detailed infrastructure assessment. Develop an infastructure checklist and trigger need for revised s7.11 or seek VPA
6 | Council Meeting Agenda is full | Additional time required. | High | Early confirmation of desired council meeting.
7
PRECINCT REZONING
RISK REGISTER
Note on B4: Smith, Adam: The cell auto updates if you change any data

## Data (hidden)
Risk Category | Consequence Type | Consequence Rating | Consequence Value | Likelihood Rating | Likelihood Value | Risk Response Type | Status | Open/Closed | Treatment Effectiveness | Treatment Value | Overall Score | Rating | Stakeholder Commitment | Commitment Value | ADKAR | Stakeholder Type | Populate of Impact/Influence |  |  |  | Comms strategy
Project - time | Financial | Catastrophic | 5 | Almost certain | 5 | Avoid | G | Open | High | 3 | 1 | Very Low | None | 1 | Developing awareness of the need for change | Individual | Combination | Impact | Influence | Result | Enlist and engage
Project - cost/financial | Operational or project | Major | 4 | Likely | 4 | Transfer | A | Closed | Moderate | 2 | 2 | Very Low | Minimal | 2 | Building desire to participate and engage with the change | Group | HL | Highly impacted | Low | Consult and collaborate | Consult and collaborate
Project - benefits | Reputational | Moderate | 3 | Possible | 3 | Mitigate | R |  | Low | 1 | 3 | Low | Low | 3 | Building knowledge of how to enact the change |  | HM | Highly impacted | Medium | Enlist and engage | Involve and inform
Project - change management | Safety | Minor | 2 | Unlikely | 2 | Accept |  |  |  |  | 4 | Low | Moderate | 4 | Realising ability to enact the change |  | HH | Highly impacted | High | Enlist and engage | Keep informed
Project - scope | Public confidence | Insignificant | 1 | Rare | 1 | [5 empty] | 5 | Moderate | High | 5 | Reinforcing changes and changed states of behaviour |  | ML | Moderately impact | Low | Involve and inform
Academic (Course load/logistics) | Compliance and regulatory | [9 empty] | 12 | Moderate | Significant | 6 |  |  | MM | Moderately impact | Medium | Consult and collaborate
Academic (Course curriculum/ quality) | Quality of service | [9 empty] | 15 | High |  |  |  |  | LH | Moderately impact | High | Enlist and engage
Academic (Research) | Other | [9 empty] | 16 | High |  |  |  |  | LL | Low or no impact | Low | Keep informed
Behaviour | [10 empty] | 20 | Critical |  |  |  |  | LM | Low or no impact | Medium | Involve and inform
Commercial Activities | [10 empty] | 25 | Critical |  |  |  |  | LH | Low or no impact | High | Consult and collaborate
Environmental
Financial
Individual
Infrastructure
International
Legal
Legislation
Market Competition and Society Changes
Organisation
Political
Projects
Reputational
Technology
Securing Success
Goal 1: A distinctively student-centred University
Goal 2: A vibrant, research-led University with regional, national and global impact
Goal 3: A unique learning experience that is innovative, flexible and responsive
Goal 4: An expanding international reach and reputation
Goal 5: A leading advocate and champion for the Greater Western Sydney region and people
Goal 6: A dynamic and innovative culture that secures success