## HOW TO USE
Wind Energy Decomissioning Calculator
Terms of use and disclaimer
This calculator is provided for use by the public including persons engaging in commercial activities.
No person or entity (including, without limitation, the State of New South Wales) associated with the development of the calculator makes any representation or warranty regarding its contents, or is liable for any loss or damage whatsoever that may result from the use of the template or any portion or variation thereof, or any other materials presented in conjunction with the calculator, or any errors or omissions in its contents.
Users of the calculator must exercise their own skill and judgment and should seek advice from suitably qualified experts, where appropriate.
The outputs of the calculator are estimations only and subject to a range of variables that can and will change overtime.
How to use
This calculator contains a range of fields that can be modified to account for the individual aspects of a project. Other fields and information are locked to provide consistent estimations. Enter information into the 'CALCULATOR TAB' to determine an estimate.
Fields that can be modified are shown in blue

## INPUT-OUTPUT
WIND TURBINE DECOMMISSION INPUTS |  |  |  |  | INPUT Guide Notes | WIND TURBINE TRIGER |  |  | INPUT Guide Notes
SECTION | DESCRIPTION | UNIT | QUANTITY | COMMENT | All Cells highlighted are INPUT variables by the user Comments column on INPUT TAB are for user commentary associated with variables | DESCRIPTION | TRIGGER |  | These YES/NO Selections allow for users to customise the calculator to consider project scope
| Overall Project Size | MW | 270 | Insert Total Mega Watts for Project | INPUT Project Power Generation in MW - used for Output Metric only | Haul Road Removal | Yes | 1 | Are haul / access raods to be removed from site? Yes will result in an increase in decommissioning costs
Tower | Number of Towers | each | 75 |  | INPUT number of wind turbine towers for the project | Underground Cable/Pit Removal | Yes | 1 | Are Underground Cables and Pit to be removed from site? Yes will result in an increase in decommissioning costs
| Average Tower Height | m | 137 | This is one function of main crane size | INPUT height of tower - used for calculating crane and overall mass per metre of tower | Concrete Foundation Removal | Yes | 1 | Are tower foundations to be removed from site? (this assumes only the depth nominated as depth below ground level is removed; not the entrie foundation. Yes will result in an increase in decommissioning costs
| Average Tower Weight | tonne | 810 |  | INPUT the overall mass of the tower | Steel and Iron Recovery | Yes | 1 | YES/NO Selection if material will be considered to be recycled. YES will result in resource recovery credits considered for the resource based on the percentage considered as an INPUT.
| Average Turbine Size | MW/turbine | 3.6 |  | INPUT of average size of turbine in MW generation per turbine unit | Aluminium and Alloy Recovery | Yes | 1 | YES/NO Selection if material will be considered to be recycled. YES will result in resource recovery credits considered for the resource based on the percentage considered as an INPUT.
| Nacelle Weight Per Turbine Size | tonne/turbine | 56 | This is onether function of main crane size | INPUT for the overall mass of the nacelle including hub, transformers, and any additional turbine weights (if not included in nacelle weight) | Copper and Alloy Recovery | Yes | 1 | YES/NO Selection if material will be considered to be recycled. YES will result in resource recovery credits considered for the resource based on the percentage considered as an INPUT.
| Blade Weight Per Tower | tonne/turbine | 26 |  | INPUT for the overall mass of blades per turbine | Polymer Recovery | Yes | 1 | YES/NO Selection if material will be considered to be recycled. YES will result in resource recovery credits considered for the resource based on the percentage considered as an INPUT.
| Surface area of foundation above ground | m2 | 20 |  | INPUT for the size of the exposed foundation, based on approximate square metres in plan to be used with the INPUT of foundation height above ground to assess the volume of foundation that is to be removed at decommissioning | Carbon/Glass Recovery | Yes | 1 | YES/NO Selection if material will be considered to be recycled. YES will result in resource recovery credits considered for the resource based on the percentage considered as an INPUT.
| Height of Foundation above Existing ground | m | 2.5 | Plan area of foundation above existing ground | INPUT of the height above ground level for the foundation as noted in the cell above for the removal at decommissioning | Electronics Recovery | Yes | 1 | YES/NO Selection if material will be considered to be recycled. YES will result in resource recovery credits considered for the resource based on the percentage considered as an INPUT.
| Depth of Foundation Below Ground To Be Removed | m | 1 |  | INPUT to assess the depth opf the foundation to be removed during decommissioning. The overal volume is based on Plan area x (Height above ground + depth below ground) | Fuels/Fluids Recovery | Yes | 1 | YES/NO Selection if material will be considered to be recycled. YES will result in resource recovery credits considered for the resource based on the percentage considered as an INPUT.
| Oil/Grease Quantity | lt/turbine | 45600 | per turbine | INPUT the litres of oils and grease within each turbine. This volume is to be removed and disposed/recycled | Concrete Recovery | Yes | 1 | YES/NO Selection if material will be considered to be recycled. YES will result in resource recovery credits considered for the resource based on the percentage considered as an INPUT.
Cable/Pits | Number of Cables in Towers | each | 3 | Assumed 3 sets of cables and the length is tower length plus 25m | INPUT the number of cables connecting to the tower and turbine (ie within the tower). This cable length + 25m is removed during decommissioning
| Number of Cables/Conduits Below Ground | each | 6 | Refer to 'Wind Turbine Trigger' table to exclude | INPUT for the number of inground cables. This is utilised for removal calculation and recycling subject to recylcing options selected in the calculator by the user
| Average Copper mass kg Per KM | kgs/km | 2.298 |  | INPUT the average mass of cable in kg/km (assumed as copper/copper alloy) for recycling /disposal calcultations subject to recycling options selected in the calculator by the user
| Average Pit Intervals along cable way | m | 250 |  | INPUT for the average pit spacing to calculate the number of pits along the cableway management network for pit removal during decommissioning
Access Road/Make Good | Access Road Quantity (Area) | m2 | 202500 |  | INPUT for the overall area of the access raods installed and to be removed decommissioning subject to the removal option selction by the user
| Access Road Base Depth | m | 0.15 |  | INPUT for the overall thickness of the access raods installed and to be removed decommissioning subject to the removal option selction by the user
| Topsoiling/Hydroseeding | m2 | 25750 | Potentially for removed access road, removed buildings and removed turbines | INPUT for the area of reseeding/topsoiling that may be required durign decommissioning to 'make good' the lands - assumption based on topsoil and hydroseeding required
Demolish | Number of Buildings To Be Demolished | each | 3 |  | INPUT for the number of ancillary buildings structures installated for the windfarm and required to be removed at decommissioning
Site Size | Overall Site Size | Ha | 1000000 |  | INPUT for the overall size of the windfarm. This is used for the Output metrics only
Mod/Demob | Number of Plants To Mobilise | each | 14 |  | INPUT the average number of plant and equipment to be mobilsed to site by Low loader or flatbed trucks. This input is used to calculate the approximate mobilisation and demobilsation costs
| Crew Size | each | 53 |  | INPUT the approximate number of personnel to be mobilised to site for decommissioning. This is to calculate the approximate mobilisation cost for the crew.
Recovery | Steel & iron Recovery | % | 88 |  | INPUT the likely percentage that is anticipted will be recycled. The remainder will be considered as disposal at a licenced waste facility and General Solid Waste.
|  | Indicative Scrap Value ($/tone) | 100 |  | INPUT the indicative rate for resource recovery
| Aluminium and Alloy Recovery | % | 1 |  | INPUT the likely percentage that is anticipted will be recycled. The remainder will be considered as disposal at a licenced waste facility and General Solid Waste.
|  | Indicative Scrap Value ($/tone) | 1000 |  | INPUT the indicative rate for resource recovery
| Copper and Alloy Recovery | % | 0.6 |  | INPUT the likely percentage that is anticipted will be recycled. The remainder will be considered as disposal at a licenced waste facility and General Solid Waste.
|  | Indicative Scrap Value ($/tone) | 5000 |  | INPUT the indicative rate for resource recovery
| Polymer Recovery | % | 4 |  | INPUT the likely percentage that is anticipted will be recycled. The remainder will be considered as disposal at a licenced waste facility and General Solid Waste.
|  | Indicative Scrap Value ($/tone) | 100 |  | INPUT the indicative rate for resource recovery
| Carbon/Glass Recovery | % | 5 |  | INPUT the likely percentage that is anticipted will be recycled. The remainder will be considered as disposal at a licenced waste facility and General Solid Waste.
|  | Indicative Scrap Value ($/tone) | 30 |  | INPUT the indicative rate for resource recovery
| Electronics Recovery | % | 0.6 |  | INPUT the likely percentage that is anticipted will be recycled. The remainder will be considered as disposal at a licenced waste facility and General Solid Waste.
|  | Indicative Scrap Value ($/tone) | 30 |  | INPUT the indicative rate for resource recovery
| Fuels/Fluids Recovery | % | 0.6 |  | INPUT the likely percentage that is anticipted will be recycled. The remainder will be considered as disposal at a licenced waste facility and General Solid Waste.
|  | Indicative Scrap Value ($/tone) | 0 |  | INPUT the indicative rate for resource recovery
Distances | Avg. Distance Between Towers | m | 500 | This will affect the productivity, productivity will be less since the inefficiency increases | INPUT for the average distance between turbines. This assists in the development of cable networks, internal mobilisation, and overall onsite movements
| Distance to Scrap/Recycle | km | 500 | This will affect the cost of transport | INPUT for the distance from site to the nearest scrap/recycling facility as part of the resource recovery calculations with respect to haulage and productivity
| Distance to Landfill | km | 500 | This will affect the cost of transport | INPUT for the distance from site to the nearest licensed waste facility for disposal haulage and productivity calculations
Project Duration | Input estimate decommissioning Duration | weeks | 45 |  | INPUT for the approximate duration of the decommissioning works
| Contractor Allowance for Margin and Overheads |  | 35% |  | INPUT for the allowance by the user for all onsite and offsite overheads, project management including supervision, and contractors profit/margin
| Risk/Contingency Allowance |  | 25% |  | INPUT Allowance for risk and contingency that might be applicable, inlcuding but not limited to wet weather, scope creep, delays etc
WIND TURBINE DECOMMISSION OUTPUTS
| DESCRIPTION | UNIT | AMOUNT | COMMENT | This Section is for Summary of the OUTPUT of decommisioning. It allows for commenting by user on the outcomes
| Total Cost Exc Recovery | $ | 104738668.2734 |  | Output of the Total Decommissioning Cost without consideration to the credits that may be achieved through resource recovery
Yes | Recovery of Material | $ | 19833038.1 |  | Subject to the YES/NO Variable by the user, this provides the approximate credit that is calculated based on the resource recovery options selected
| Total Cost After Recovery | $ | 84905630.1734 |  | Output of the Total Decommissioning Cost with consideration to the credits that may be achieved through resource recovery (if applicable)
| Cost Per MW Exc Recovery | $/MW | 387920.9936 |  | OUT metric for decommissioning costs on a per MW basis excluding resource reciovery credits
| Cost Per MW Inc Recovery | $/MW | 314465.2969 |  | OUT metric for decommissioning costs on a per MW basis including resource reciovery credits
| Cost Per Turbine Exc Recovery | $/turbine | 1396515.577 |  | OUT metric for decommissioning costs on a per Turbine/Tower basis excluding resource reciovery credits
| Cost Per Turbine Inc Recovery | $/turbine | 1132075.069 |  | OUT metric for decommissioning costs on a per Turbine/Tower basis including resource reciovery credits

## ESTIMATE
DECOMMISSIONING OF WIND TURBINE DIRECT JOB COST
ITEM NO | DESCRIPTION | CREW | UNIT | QUANTITY | RATE PER UNIT | PRODUCTIVITY PER UNIT | DURATION (DAYS) | TOTAL AMOUNT ($) | COMMENT | NO CREWS | NO MEN IN A CREW | TOTAL MEN
1 | Electrical Works | Electrical Works Total | each | 75 | 1640 | 4 | 19 | 31160 | Assumed 4 Turbines Per Day- Isolate each Turbine | 1 | 2 | 2 | INPUT Guide Notes
2 | Removal of Liquid | Fluid Removal Total | lt | 3420000 | 5850 | 75000 | 46 | 269100 | production rate is based on 75,000lt of oils removed per day | 1 | 6 | 6 | • Decommissioning scope has been broken down to the key elements/tasks with each task containing a subset of works crews to perfomr the works. Estimates for crews are provided on the CREWS TAB • Quantities are calculated for the INPUT by the user on the INPUT-OUT TAB, and adjusted by assumptions as detailed in the comments for items such as density •Productovities per unit are based on assumptions iusing reasonable productivities that can be achieved by the sets for crews provided on the CREWS TAB •All concrete is recycled at $20/tonne base don typical rates •All steel is recycled at $100/tonne resource recovery based on avergae rates
2 | Cable Removal | Cable Removal Crew | m | 261450 | 3250 | 7500 | 35 | 113750 |  | 1 | 4 | 4
3 | Removal of Turbine/Blades/Tower | Turbine Crew | Each | 75 | 48490 | 0.5 | 150 | 7273500 | Remove Turbine & Blades 2 days to disassemble | 2 | 8 | 16
|  | Turbine Crew | Each | 75 | 48490 | 1 | 75 | 3636750 | Disassemble Tower 1 tower per day
|  | Internal Mob/Demob | Each | 74 | 75630 | 1 | 3 | 5596620 | Internal relocation, prestart, travel, inefficiency - 3 days for lattice crane crews
4 | Removal of Turbine Concrete Footing | Concrete Crew Total | m3 | 5250 | 6550 | 25 | 21 | 137550 | Assumed 25m3 per hr demolition for all concrete demolished. Noting only demolished to the depth input by user | 1 | 2 | 2
|  | Concrete Disposal Crew | tonne | 13125 | 18150 | 100 | 14 | 254100 | Density of concrete 2.45t/m3
|  | Disposal Fee | tonne | 11625 |  |  |  |  | Information ONLY - Not Used
|  | Recovery Steel | tonne | 1155 |  |  |  |  | Information ONLY - Not Used
|  | Backfill Crew | m3 | 1500 | 7750 | 200 | 7.5 | 58125 | Site won material - from onsite borrow pit - maybe reused access road material | 1 | 1 | 1
5 | Removal Of Conduits/Cables | Conduit Crew Total | m | 37500 | 8400 | 20 | 188 | 1579200 | 8 conduits removed & Backfilled 20m Per hr | 2 | 2 | 4
|  | Pit Crew Total | Each | 150 | 8550 | 1 | 15 | 128250 | Assume Concrete pit - 900x900 pit | 1 | 2 | 2
|  | Conduit Disposal - T&D | m | 37500 | 1750 | 250 | 150 | 262500 | One T&D can carry 750m of used conduit.
|  | Disposal Fee - conduits | tonne | 108570 | 65 |  |  | 7057050 | The weight of 50mm conduit per m is around 0.78kg and it is assumed that there 4 conduits to be removed
|  | Disposal Fee -pits | tonne | 150 | 0 |  |  | 0 | The weight of 63mm conduit per m is around 1.2kg.
6 | Removal of Access Road | Road/Crane Pad Crew | m2 | 202500 | 9850 | 120 | 169 | 1664650 | Assumed cables are by the road and 5m wide | 3 | 1 | 3
|  | Road Material Disposal | m3 | 28875 | 32150 | 30 | 97 | 3118550 | Assumed road formation assumed 150mm recovered and topdressed | 2 | 1 | 2
|  | Disposal Fee | tonne | 51975 | 60 |  |  | 3118500
7 | Removal of Buildings | Building Crew | Each | 1 | 11250 | 20 | 20 | 225000 | Assumed 50 tonne debris per building and in total 3 buildings. One admin, two electrical | 1 | 4 | 4
|  | Concrete Disposal Crew | tonne | 150 | 18150 | 100 | 2 | 36300 |  | 1 | 1 | 1
|  | Disposal Fee | tonne | 150 | 300 |  |  | 45000
8 | Break Down Tower & Turbine | Breakdown Crew | tonne | 60750 | 13090 | 1619.34 | 37.5153 | 491075.0676 | Breakdown the Tower to 26tonne loads. Productivity is cutting two towers per day. | 1 | 6 | 6
|  | Breakdown Crew | tonne | 17070 | 13090 | 1250 | 13.656 | 178757.04 | Breakdown turbine to 26 tone loads
|  | Internal Mob/Demob | each | 74 | 75630 | 1 | 3 | 16789860 | 3 days to relocate the 750t crane for each tower
8 | Transport Turbine Material Off Site | Turbine Material Disposal | tonne | 77820 | 175 | 13.6033 | 40715.8231 | 7125269.0385 | For one truck
|  | Disposal Fee | tonne | 77820 | 0 |  |  | 0 | Refer Below
9 | Topsoiling | Topsoil Crew | m2 | 25750 | 6550 | 150 | 18 | 117900 | Assumed for removed access road, removed buildings and removed turbines
10 | Hydroseeding |  | m2 | 25750 | 3 |  |  | 77250
11 | Mobilisation | Plant & Equipment | Each | 14 | 15000 |  |  | 210000 | Assumed 4xExc, 2xRoller, 4xTipper, 1xGrader,3xWatercart
|  | Personnel | Each | 53 | 2100 |  |  | 111300 | Total number of labour to be mobilised, not all of them will be on the site at the same time. Assumed that 10 hours mob, 10 hours demob and 8 hour induction
|  | Mobile 750T | Each | 1 | 400000 |  | 2 | 800000 | $400,000 confirmed rate to mobilise on East Coast of Australia each way
|  | Mobile 250T | Each | 0 | 45000 |  | 2 | 0
|  | Mobile 200T | Each | 2 | 45000 |  | 2 | 180000 | Mobilisation of 2 support cranes |  |  | 53
12 | Landfill Disposal | Disposal Fee | tonne |  | 300 |  |  | 0
TOTAL DIRECT JOB COST | [7 empty] | 60687066.1461
DECOMMSSIONING OF WIND TURBINE INDIRECT JOB COST
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE |  |  |  | AMOUNT | COMMENT
1 | Establishment of Envrionmental Protection | m | 8400 | 7.5 |  |  |  | 63000 | Refer Crew Sheet
2 | Maintenance of Environmental Protection | week | 45 | 1500 |  |  |  | 67500 | Duration as input, and $1,500 typical expense allowed for maintenance and repairs after storm events
3 | Construction of Site Office Establishment | LS | 1 | 200000 |  |  |  | 200000 | $200,000 assumed for establishent of site
3 | Construction of Site Office Demob | LS | 0.33 | 200000 |  |  |  | 66000 | Disestablishment of site is 33% of establishment costs
3 | Construction of Site Office recurring cost | week | 45 | 15000 |  |  |  | 675000 | $15,000 recurring costs for site running per week
4 | Traffic Management | LS | 0.5% | 61758566.1461 |  |  |  | 308792.8307 | 0.5% of Base Estimate
TOTAL INDIRECT JOB COST | [7 empty] | 1380292.8307
[7 empty] | Subtotal | 62067358.9768
[7 empty] | Uplift Margin & Overheads | 21723575.6419
83790934.6187
[7 empty] | Risk Allowance/Contingency | 20947733.6547
104738668.2734
[7 empty] | Price per Tower | 1396515.577
| RECOVERY OF MATERIALS |  | UNIT | QUANTITY | RATE |  | Recover | AMOUNT |  |  |  |  | Material type | Proportion of turbine mass | Assumed pathway is to^^: | Estimated recovery rate | Illustrative scrap value ($/tonne) ## | Estimated recovery as a % of turbine mass
| Cables (Copper and Alloy) | based on 2,298kgs/km | tonne | 1067.7321 | 5000 |  | 1 | 5338660.5 |  |  |  |  | Steel and iron materials | 88% | Scrap metal facility | 98% | 100 | 86.2%
| Steel |  | tonne | 130386.6 | 100 |  | 1 | 13038660 |  |  |  |  | Aluminium and alloys | 1% | Scrap metal facility | 98% | 1000 | 1%
| Aluminium and Alloys |  | tonne | 778.2 | 1000 |  | 1 | 778200 |  |  |  |  | Copper and alloys | 0.6% | Scrap metal facility | 98% | 5000 | 0.6%
| Liquids | Recover - Nil Cost - 700kg/m3 | tonne | 2394 | 0 |  | 1 | 0 |  |  |  |  | Polymer materials | 0.04 | Landfill | N/A | 100 | N/A
| Concrete materials | – scrap value is $20/tonne | tonne | 11775 | 20 |  | 1 | 235500 |  |  |  |  | Carbon / glass composites | 0.05 | Landfill | N/A | 30 | N/A
| Polymer Material | Landfill | tonne | 3112.8 | 100 |  | 1 | 311280 |  |  |  |  | Electronics / electrics | 0.006 | Landfill | N/A | 30 | N/A
| Electronics | Landfill | tonne | 466.92 | 30 |  | 1 | 14007.6 |  |  |  |  | Fuels and fluids | 0.006 | Landfill | N/A | 0 | N/A
| Carbon/ Glass Composites | Landfill | tonne | 3891 | 30 |  | 1 | 116730 |  |  |  |  | Residual Waste | 0.002 | Landfill | N/A | N/A | N/A
| ^^ for material sent to landfill, assume a landfill disposal cost of $300/tonne | [11 empty] | Overall | 100% |  |  |  | 87.8%
| ## assumed scrap values are likely to be conservative | [5 empty] | Total Recovery | 19833038.1 |  |  |  |  | ^^ for material sent to landfill, assume a landfill disposal cost of $300/tonne
| ** for the concrete foundations, assume all material is sent to a recovery facility – scrap value is $20/tonne | [11 empty] | ## assumed scrap values are likely to be conservative
** for the concrete foundations, assume all material is sent to a recovery facility – scrap value is $20/tonne
[7 empty] | Total | 84905630.1734
[7 empty] | per Tower | 1132075.069

## CREWS
LABOUR RATES USED | [5 empty] | CREW RATES PER DAY
DESCRIPTION | UNIT | RATE | COMMENT |  |  | DESCRIPTION | INCLUSION | UNIT | QTY | RATE | TOTAL RATE PER DAY | COMMENT
LAB-CW2 | HR | 65 | General Labour |  |  | Electrical Works | LAB-CW5 | hr | 20 | 82 | 1640 | 2 man crew
LAB-CW3 |  | 75 | Fitter |  |  | Electrical Works Total |  |  |  |  | 1640
LAB-CW5 |  | 82 | Qualified Trade
LAB-CW6 |  | 86 | Operator |  |  | Liquid Waste removal | Liquid Waste Specialist | hr | 10 | 110 | 1100
Liquid Waste Specialist |  | 110 | Liquid Waste Specialist |  |  | Fitter | LAB-CW3 | hr | 40 | 75 | 3000 | 4 man crew
[6 empty] | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2 man crew
Hours Per Day | hr | 10 |  |  |  | Tools | Small Tools | hr | 30 | 15 | 450
[6 empty] | Fluid Removal Total |  |  |  |  | 5850
PLANT RATES USED | [5 empty] | Excavator | Excavator 30T | hr | 10 | 175 | 1750
DESCRIPTION | UNIT | RATE | COMMENT |  |  | Concrete Breaker | Hammer 30T | hr | 10 | 20 | 200
Excavator 30T | hr | 175 |  |  |  | Tipper | Tipper 20T | hr | 20 | 150 | 3000 | Taking the concrete to site stockpile
Excavator 20T | hr | 160 |  |  |  | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2man crew
Hammer 30T | day | 200 |  |  |  | Tools | Small Tools | hr | 20 | 15 | 300
Hammer 20T | day | 150 |  |  |  | Concrete Crew Total |  |  |  |  | 6550
Tipper 20T | hr | 150
Roller 15-20T | hr | 120 |  |  |  | Excavator | Excavator 20T | hr | 10 | 160 | 1600
Watercart 12-15KL | hr | 130 |  |  |  | Tipper | Tipper 20T | hr | 20 | 150 | 3000 | Taking the concrete to site stockpile
Grader 140 | hr | 210 |  |  |  | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2 man crew
Small Tools | hr | 15 |  |  |  | Roller | Roller 15-20T | hr | 10 | 120 | 1200
Mobile Lattice 750T | hr | 2521 | complete crew rate |  |  | Watercart | Watercart 12-15KL | hr | 10 | 130 | 1300
Mobile 250T | hr | 1100
Mobile 200T | hr | 850 |  |  |  | Conduit Crew Total |  |  |  |  | 8400
Mobile 150T | hr | 750
Boom lift 40m | day | 480 |  |  |  | Excavator | Excavator 20T | hr | 10 | 160 | 1600
T&D | hr | 175 |  |  |  | Tipper | Tipper 20T | hr | 20 | 150 | 3000 | Taking the concrete to site stockpile
Road Train/Semi Trailer | hr | 200 |  |  |  | Grader | Grader 140 | hr | 10 | 210 | 2100
Oxy Cutter | hr | 12 |  |  |  | Roller | Roller 15-20T | hr | 10 | 120 | 1200
[6 empty] | Watercart | Watercart 12-15KL | hr | 10 | 130 | 1300
NO TRUCKS CONCRETE DISPOSAL | [5 empty] | Labour | LAB-CW2 | hr | 10 | 65 | 650
Distance | km | 500 |  |  |  | Road/Crane Pad Crew |  |  |  |  | 9850
Speed | km/hr | 80
T&D Capacity | tonne | 30 |  |  |  | Excavator | Excavator 30T | hr | 10 | 175 | 1750 | One excavator breaking, one excavator loading
Concrete Loading PR | m3/hr | 10 |  |  |  | Excavator | Excavator 30T | hr | 10 | 175 | 1750
Loading Time | min | 100 |  |  |  | Concrete Breaker | Hammer 30T | hr | 10 | 200 | 2000
Haulage Time | min | 750 |  |  |  | Tipper | Tipper 20T | hr | 20 | 150 | 3000
Unloading | min | 15 |  |  |  | Labour | LAB-CW2 | hr | 40 | 65 | 2600 | 4 man crew
Change Trucks | min | 1.2 |  |  |  | Tools | Small Tools | hr | 10 | 15 | 150
Total Cycle Time | min | 866.2 |  |  |  | Building Crew |  |  |  |  | 11250
Number of Trucks | each | 9 |  | mass | height
|  |  |  | 1 | 1 | Main Crane | Mobile Lattice 750T | hr | 10 | 2521 | 25210 | 750t mobile Lattice crane adopted with full service crew
|  |  |  | 0 | 0 | Main Crane | Mobile 250T | hr | 0 | 1100 | 0
NO TRUCKS ROAD MATERIAL DISPOSAL | [5 empty] | Support Crane | Mobile 200T | hr | 20 | 850 | 17000 | 2 support cranes required
Distance | km | 500 |  |  |  | Lift | Boom Lift 40m | day | 10 | 48 | 480
Speed | km/hr | 80 |  |  |  | Rigger | LAB-CW3 | hr | 60 | 75 | 4500 | 6 man crew
T&D Capacity | tonne | 30 |  |  |  | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2 man crew
Loading PR | m3/hr | 20 |  |  |  | Turbine Crew |  |  |  |  | 48490
Loading Time | min | 50 |  |  |  | Internal Mobilisation |  | each | 1 | 75630 | 75630 | Based on 3 days per mobilisation with full crew confirmed required for each mobilisation
Haulage Time | min | 750
Unloading | min | 15 |  |  |  | Truck | T&D | hr | 90 | 175 | 15750
Change Trucks | min | 1.2 |  |  |  | Excavator | Excavator 30T | hr | 10 | 175 | 1750 | Per day PR is 30x10=300m3. Hence one excavator can load up to 750tonne/30 = 25 trucks
Total Cycle Time | min | 816.2 |  |  |  | Labour | LAB-CW2 | hr | 10 | 65 | 650
Number of Trucks | each | 17 |  |  |  | Concrete Disposal Crew |  |  |  |  | 18150
[6 empty] | Truck | T&D | hr | 170 | 175 | 29750
Recovery of Materials | Yes |  |  |  |  | Excavator | Excavator 30T | hr | 10 | 175 | 1750 | Per day PR is 75*10=750m3 per day. Hence one excavator can load up to 1350tonne/30 = 45 T&D
| No |  |  |  |  | Labour | LAB-CW2 | hr | 10 | 65 | 650
[6 empty] | Road Material Disposal |  |  |  |  | 32150
[6 empty] | Crane | Mobile 150T | hr | 20 | 750 | 15000
[6 empty] | Truck | Road Train/Semi Trailer | hr | 170 | 200 | 34000 | Assumed that tower will be transported in 4 pieces, generator will be transported in 10 pieces and blades in 3 pieces. Hence, there will be 17 truck loads for one turbine
[6 empty] | Rigger | LAB-CW3 | hr | 40 | 75 | 3000
[6 empty] | Labour | LAB-CW2 | hr | 10 | 65 | 650
[6 empty] | Turbine Material Disposal |  |  |  |  | 52650
[6 empty] | Excavator | Excavator 20T | hr | 10 | 160 | 1600
[6 empty] | Tipper | Tipper 20T | hr | 20 | 150 | 3000
[6 empty] | Watecart | Watercart 12-15KL | hr | 10 | 130 | 1300
[6 empty] | Labour | LAB-CW2 | hr | 10 | 65 | 650
[6 empty] | Topsoil Crew |  |  |  |  | 6550
[6 empty] | Fitter | LAB-CW3 | hr | 20 | 75 | 1500 | 2 man crew
[6 empty] | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2 man crew
[6 empty] | Tools | Small Tools | hr | 30 | 15 | 450
[6 empty] | Cable Removal Crew |  |  |  |  | 3250
[6 empty] | Excavator | Excavator 20T | hr | 10 | 160 | 1600
[6 empty] | Tipper | Tipper 20T | hr | 20 | 150 | 3000
[6 empty] | Roller | Roller 15-20T | hr | 10 | 120 | 1200
[6 empty] | Watercart | Watercart 12-15KL | hr | 10 | 130 | 1300
[6 empty] | Labour | LAB-CW2 | hr | 10 | 65 | 650 | 1 man crew
[6 empty] | Backfill Crew |  |  |  |  | 7750
[6 empty] | Excavator | Excavator 20T | hr | 10 | 160 | 1600
[6 empty] | Hammer | Hammer 20T | hr | 10 | 15 | 150
[6 empty] | Tipper | Tipper 20T | hr | 20 | 150 | 3000
[6 empty] | Labour | LAB-CW2 | hr | 20 | 65 | 1300
[6 empty] | Roller | Roller 15-20T | hr | 10 | 120 | 1200
[6 empty] | Watercart | Watercart 12-15KL | hr | 10 | 130 | 1300
[6 empty] | Pit Crew Total |  |  |  |  | 8550
[6 empty] | Crane | Mobile 150T | hr | 10 | 750 | 7500
[6 empty] | Lift | Boom Lift 40m | day | 10 | 48 | 480
[6 empty] | Rigger | LAB-CW3 | hr | 40 | 75 | 3000 | 4 man crew
[6 empty] | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2 man crew
[6 empty] | Oxy Cutter | Oxy Cutter | hr | 30 | 12 | 360
[6 empty] | Small Tools | Small Tools | hr | 30 | 15 | 450
[6 empty] | Breakdown Crew |  |  |  |  | 13090
[6 empty] | Silt Fence Supply and Install |  | m | 8400 | 7.5 | 63000 | length of silt fence is based on 2 sides of the overall access road and + 100m per turbine site
[6 empty] | Establishment of Envrionmental Protection |  |  |  |  | 63000 | Rate of $7.5/m is typical cost to suply and install silt fencing